## Sheet1
Task ID | Task Name | Team | Deadline
D01 | Home Page design | Design | 3 days
D02 | Book Free Consultation / Discovery call / Lead generation design | Design | 3 days
D03 | Package / Plans design | Design | 3 days
D04 | Body Type & Health / Diet Guide design | Design | 3 days
D05 | Logo design | Design | 3 days
D06 | About Client / Poshan design | Design | 3 days
D07 | Blogs design | Design | 3 days
D08 | Our Partners (Tentative) design | Design | 3 days
D09 | Diet Survey design | Design | 3 days
D10 | FAQ design | Design | 3 days
D11 | Admin Portal design | Design | 3 days
Dev01 | Home Page development | Development | 4 days
Dev02 | Book Free Consultation / Discovery call / Lead generation development | Development | 4 days
Dev03 | Package / Plans development | Development | 4 days
Dev04 | Body Type & Health / Diet Guide development | Development | 4 days
Dev05 | Logo development | Development | 4 days
Dev06 | About Client / Poshan development | Development | 4 days
Dev07 | Blogs development | Development | 4 days
Dev08 | Our Partners (Tentative) development | Development | 4 days
Dev09 | Diet Survey development | Development | 4 days
Dev10 | FAQ development | Development | 4 days
Dev11 | Admin Portal development | Development | 4 days
Test01 | Home Page testing | Testing | 1 day
Test02 | Book Free Consultation / Discovery call / Lead generation testing | Testing | 1 day
Test03 | Package / Plans testing | Testing | 1 day
Test04 | Body Type & Health / Diet Guide testing | Testing | 1 day
Test05 | Logo testing | Testing | 1 day
Test06 | About Client / Poshan testing | Testing | 1 day
Test07 | Blogs testing | Testing | 1 day
Test08 | Our Partners (Tentative) testing | Testing | 1 day
Test09 | Diet Survey testing | Testing | 1 day
Test10 | FAQ testing | Testing | 1 day
Test11 | Admin Portal development | Testing | 1 day